## Sheet1
Masterplan sample
|  |  | RACI | [6 empty] | Weeks 2025
Functional Area | Item | Detail | Responsible | Accountable | Consulted | Informed | Start Dates | Estimated Date of Completion | Revised Date of Completion | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Finance | Budget | Initial meetings to discuss budget | HPD | TM | Med, HC, OC, OM | Finance | 2024-11-01 | 2024-12-01
|  | Finalise Team budget and submitt | TM | Finance |  | Sqd | 2024-12-05
|  | Revision of Team budget every month | TM | HPD, Finance | AS |  | 2025-01-02 | 2025-12-01 | bar: Weeks 2025 1; Weeks 2025 6; Weeks 2025 10; Weeks 2025 14; Weeks 2025 18; Weeks 2025 22; Weeks 2025 27; Weeks 2025 31; Weeks 2025 35; Weeks 2025 40; Weeks 2025 44; Weeks 2025 49
|  | Reset 2026 budget | HPD | TM | Med, HC, OC, OM | Finance | 01/11/202 | 2025-12-01 | bar: Weeks 2025 44; Weeks 2025 49
Knowledge Transfer | Safeguarding | Review safeguarding policies
| Equipment | Review Team equipment
| Equipment | Confirm any repurchase necessary
| Equipment | Review materplan
| Squad pack | Squad info pack review/initiation
| Squad pack | Review policies for Squad info pack
| Squad pack | Issue squad info pack
| Checklists | Review daily schedules
| Checklists | Review checklists
| Checklists | Review contact details
| Checklists | Review daily duty list
| Reporting | Compile list of reports and allocate
| Reporting | Completion of reports
| Reporting | Review for calibration
Campaign Planning | Preparation | Confirm meetings to review/establish campaign plan
| Review | Revise and adjust
| Communicate | Issue to relevant squad members
Regulations | Terms of Participation | Read the Terms of Participation
| Terms of Participation | Send out relevant information to Leads
| Anti Doping | Whereabouts information
| Anti Doping | Activity log
| E-Learning | Squad members e-learning complete
| Laws | Law trials
Squad information | Checklist | Compile checklist of squad members
| Squad details | Squad stats
| Squad details | Headshots
| Squad details | Biographics
| Squad details | Phonetic guides
| Squad details | Recorded pronunciation
| Medical details | Medical Information TUE
| Medical details | Medical Information Cardiac Screening
| Medical details | Medical Information HIA Baselines
| Medical details | ICIR II Qualifications for Medics
| Kit | Kit sizing
| Passport | Passport copies
| Passport | Passport dates checklist set up
| Food | Food preferences, requirements, allergies
Kit | Requirements | Outline requirements
| Designs | Agree colours / designs
| Receipt | Receipt of kit
| Kit out | Kit out squad memebers
| Policy | Clothing policy issued
Other informaiton | Insurance | Insurance policy details
| Insurance | Insurance copies
| Commercial | Commercial obligations for squad confirmed
| Commercial | Additional travel/camp requirements
| Media | Cadence of media activity agreed
Camp/ Tournment | Flights | Flights research
| Flights | Flights booked
| Visa | Visa requirements research
| Visa | Visa requirements issued to squad
| Accommodation | Accommodaiton review of requirements
| Accommodation | Accommodation numbers and configuration confirmed
| Accommodation | Accommodation booked
| Food | Review menues
| Food | Relay dietry requirements
| Food | Confirm menu adjustment
| Water | Water provision confirmed
| Water | Isotonic provision confirmed
| Water | Delivery schedule confirmed
| Ice | Ice provision confirmed
| Ice | Delivery schedule confirmed
| Laundry | Laundry provision confimed
| Laundry | Pick up / dleivery schedule confirmed
| Laundry | Clothing assignment confirmed
| Training venues | Venue requirements confirmed
| Training venues | Proposed training venues reviewed
| Training venues | Training venue confirmed
| Equipment | Travelling equipement list confirmed
| Equipment | Rent, purchase, borrow on site researched
| Equipment | Shipping confirmed
| Accreditation | Application complete
| Accreditation | Review application for possible changes
| Security | Confirm security requirements
| Meeting and Events | Diary of events compiled
| Meeting and Events | Necessary attendees confirmed
| Meeting and Events | Reminders schedule
| Other | Drone requlations confirmed
| Other | Filming regulations confirmed
| Other | Team tickets confirmed
| Other | Cultural research
| Other | Down time activities
| Other | Daily meeting schedule

## Legend
Legend
Team Manager | TM
HP Director | HPD
Medical | Med
Head Coach | HC
Other Coaches | OC
Other Management | OM
Players | Plyr
All Staff | AS
All Squad | Sqd